Contents

[Requirements 2](#_Toc387435859)

[Assumptions 2](#_Toc387435860)

[Effort Estimate 2](#_Toc387435861)

[Development Effort 2](#_Toc387435862)

[Engagement Effort Summary 3](#_Toc387435863)

# Requirements

Section on the detail page of Opportunity with the following capabilities

1. Mass Edit
2. Add New Row to insert new record
3. Mass Update,
4. Delete on Particular Record,
5. View Particular Record through Pop-up

# Assumptions

1. Mass Update would not be supported in the current development.

# Effort Estimate

The below table outlines the ballpark effort and may vary depending upon the actual requirements at the time of implementation.

### Development Effort

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Item No.** | **Item Description** | **Category** | **Solution Overview** | **Complexity Level** | **Development Efforts(Hrs)** |
| 1 | Sales History | Custom Development | Visualforce page with a editable grid to display Bank Statement and Credit Card Sales | Complex | 16 |
| 2 | Submission | Custom Development | Visualforce page with a editable grid to display Submission records | Medium | 10 |
| 3 | Offer | Custom Development | Visualforce page with a editable grid to display Offer records | Medium | 6 |
| 4 | Stips | Custom Development | Visualforce page with a editable grid to display Stips records | Medium | 6 |
| 5 | Commissions | Custom Development | Visualforce page with a editable grid to display Commission and the associated Payable, Payable Line Item, Receivable, Receivable Line Item Summary records | Very Complex | 32 |
| 6 | Syndication | Custom Development | Visualforce page with a editable grid to display Syndication records | Medium | 6 |
| 7 | Loan Balance | Custom Development | Visualforce page with a editable grid to display Loan Balance records | Medium | 6 |
| 8 | Contact Roles | Custom Development | Visualforce page with a editable grid to display Contact Roles records | Medium | 6 |
| 9 | Task | Custom Development | Visualforce page with a editable grid to display Task records | Simple | 6 |
| 10 | Test Code Development | Custom Development | Apex test code for the developed business logic | Medium | 16 |
| **Total Development Effort (Hrs.)** | | | | | **110** |

### Engagement Effort Summary

|  |  |  |  |
| --- | --- | --- | --- |
| **Engagement Effort Summary** | | | |
| **No** | **Project Phase** | **%** | **Efforts (Hrs)** |
| 1 | Project Management | 3% | 4 |
| 2 | RA & Solution Design | 0% | 0 |
| 3 | Development & Unit testing | 80% | 110 |
| 4 | Integration and System Testing | 15% | 21 |
| 5 | Deployment & Documentation | 2% | 3 |
| 6 | UAT Support, Go-Live | 0% | 0 |
| **Total Project Efforts** | | 100% | **138** |