## Summary
Engagement Effort Summary |  |  |  | Activity | Total Effort | Weekly/Monthly Schedule | [5 empty] | Go-Live | Warranty/Support
No | Project Phase | % | Efforts (Hrs) |  |  | W1 | W2 | W3 | W4 | W5 | W6 |  | W7 | W8
1 | Project Management | 4% | 6 | Project Management | 6 | 2 | 2 | 2
2 | RA & Solution Design | 8% | 11 | RA & Solution Design | 11 | 11
3 | Development & Unit testing | 70% | 97 | Development | 97 | 28 | 69
4 | Integration and System Testing | 15% | 21 | Integration and System testing | 21 |  |  | 21
5 | Deployment & Documentation | 3% | 4 | Deployment & Documentation | 4 |  |  | 4
6 | UAT Support, Go-Live | 0% | 0 | UAT Support, Go-Live | 0
7 | Live rollout support [warranty period 2 weeks] | 0% | 0 | Live rollout support | 0 | [8 empty] | 0
Total Project Efforts |  | 100% | 138.5714 | 0 | 139 | 41 | 71 | 27 |  |  |  |  | 1 | 1
Total Engagement Efforts |  |  | 139 | Resources |  | 3 | 3 | 3
Blended Rate (USD Per Hour)
Cost (USD) |  |  | 0

## WBS
Item No. | Item Description | Category | Solution Overview | Complexity Level | POC Efforts | Development Efforts(Hrs) | Assumptions
1 | Data Model Changes | Configuration | Creating additional objects / fields required to hold the necessary information | Simple |  | 4
2 | ACH WSDL Consumption | Custom Development | Consuming the SOAP WSDL to generate Apex classes by modifying the SOAP endpoint and port binding in WSDL | Simple |  | 1
3 | Performing Credits to Merchants, Paying Commissions, Sales Reps and ISOs | Custom Development | User interface with the ability to provide one time payment details and Apex controller code to perform the callouts to the ACH works service | Medium |  | 18 | Assumes that a single payment would be done manually by User using the custom developed user interface
4 | Performing Debits to getting payments from Merchants, either payback or payment of fees | Custom Development | User interface with the ability to provide one time payment details and Apex controller code to perform the callouts to the ACH works service | Medium |  | 16 | Assumes that a single payment would be done manually by User using the custom developed user interface
5 | Ability to Schedule Payments | Custom Development | Visualforce Page to schedule a payment and Batch Job to execute one time payment as scheduled - Daily / Weekly | Complex |  | 30
6 | Performing Refunds | Custom Development | User interface to select the transaction to reverse and perform a callout to perform credit | Medium |  | 14 | Assumes it is the same as performing a credit. The ACH Works does not have a direct ability to refund or reverse the payments
7 | Test Code Development | Custom Development | Apex test code for the developed business logic | Medium |  | 14
97