## Summary
Engagement Effort Summary |  |  |  | Activity | Total Effort | Weekly/Monthly Schedule | [5 empty] | Go-Live | Warranty/Support
No | Project Phase | % | Efforts (Hrs) |  |  | W1 | W2 | W3 | W4 | W5 | W6 |  | W7 | W8
1 | Project Management | 3% | 3 | Project Management | 3 | 1 | 1 | 1
2 | RA & Solution Design | 0% | 0 | RA & Solution Design | 0
3 | Development & Unit testing | 80% | 68 | Development | 68 | 40 | 28
4 | Integration and System Testing | 14% | 12 | Integration and System testing | 12 |  | 12
5 | Deployment & Documentation | 3% | 3 | Deployment & Documentation | 3 |  |  | 3
6 | UAT Support, Go-Live | 0% | 0 | UAT Support, Go-Live | 0
7 | Live rollout support [warranty period 2 weeks] | 0% | 0 | Live rollout support | 0 | [8 empty] | 0
Total Project Efforts |  | 100% | 85 | 0 | 86 | 41 | 41 | [5 empty] | 1 | 1
Total Engagement Efforts |  |  | 86 | Resources |  | 2 | 2
Blended Rate (USD Per Hour)
Cost (USD) |  |  | 0

## WBS
Item No. | Item Description | Category | Solution Overview | Complexity Level | POC Efforts | Development Efforts(Hrs) | Assumptions
1 | Data Model Changes | Configuration | Creating additional objects / fields required to hold the following information. 1. Registered Payment gateway unique code 2. Transaction Reference No 3. Merchant Username / Password | Simple |  | 2 | The only type pf payment transactions supported would be One Time Payment and Void
2 | ACH WSDL Consumption | Custom Development | Consuming the SOAP WSDL to generate Apex classes by modifying the SOAP endpoint and port binding in WSDL | Simple |  | 2
3 | EFT Payment Validation | Custom Development | Apex Code to validate the account for performing EFT Transfers | Complex |  | 20 | The only type pf payment transactions supported would be One Time Payment and Void
4 | Payment Processing for Single Transaction | Custom Development | Apex Code to perform fund transfer | Complex |  | 20 | The only type pf payment transactions supported would be One Time Payment and Void
5 | Payment Processing for Void Transaction | Custom Development | Apex Code to void a particular transaction | Medium |  | 12 | The only type pf payment transactions supported would be One Time Payment and Void
6 | Test Code Development | Custom Development | Apex test code for the developed business logic | Medium |  | 12
68