## List of Components
Transaction_LineItemAmountExceedsTransactionAmount | Account Record Types
Sr. No. | Name | Type | API Name | Parent | Description
1 | Bank
2 | ISO
3 | Merchant
4 | Merchant Processor/Bank
5 | Processor
6 | Vendor
Account Page Layouts
Sr. No. | Name | Type | API Name | Parent | Description
1 | Merchant
2 | Vendor Account Layout
Renewal Functionality
Sr. No. | Name | Type | API Name | Parent | Description
1 | Term (Months) | Custom Field |  | Opportunity
2 | ACH Pmt amount | Custom Field |  | Opportunity
3 | Date Contract Signed | Custom Field |  | Opportunity
4 | Commission % | Custom Field |  | Opportunity
5 | Contract_Requested_Date | Custom Field |  | Opportunity
6 | Anticipated Renewal Date | Custom Field |  | Contract
7 | Current Balance Amt. | Custom Field | Currency | Contract
8 | Current Balance Date | Custom Field |  | Contract
9 | Opportunity | Custom Field |  | Contract
10 | Opportunity(Renewal) | Custom Field |  | Contract
11 | Renewal Eligibility (Days from funding) | Custom Field |  | Contract
12 | Stage | Custom Field |  | Contract
13 | Deal Type | Custom Field |  | Contract
Deal Entry Wizard
Sr. No. | Name | Type | API Name | Parent | Description
1 | CreateContract | Visualforce Page
2 | CreateContractController | Class
3 | CreateContractControllerTest | Apex Class
4 | Deal Entry Wizard | Button on Opportunity |  | Opportunity
5 | BankAssets_Resources | Static Resource
6 | Opportunity | Standard Object
7 | CreateContract_InitialStage | Custom Label
8 | CreateContract_NoSubmissionNOfferErr | Custom Label
9 | CreateContract_StageFunded | Custom Label
10 | CreateContract_CannotSwitchOffer | Custom Label
11 | Contract | Standard Object
12 | Payable | Custom Object
13 | Receivable | Custom Object
14 | Syndication | Custom Object
15 | Field Names | custom setting
Submission Wizard
Sr. No. | Name | Type | API Name | Parent | Description
1 | Name | Standard Field | Name | Account
2 | Industry | Standard Field | Industry | Account
3 | Credit Score | Standard Field | Credit_Score__c | Opportunity
4 | Years in Business | Standard Field | Years_in_Business__c | Account
5 | Gross monthly Sales | Standard Field | Gross_monthly_Sales__c | Account
6 | Amount Requested | Standard Field | Amount_Requested__c | Opportunity
7 | Program | Custom Object | Program__c | Program
8 | Credit Score |  | Credit_Score__c | Program
9 | Years in Business |  | Years_in_Business__c | Program
10 | Min. Monthly Deposits |  | Min_Monthly_Deposits__c | Program
11 | Industry |  | Industry__c | Program
12 | Preffered Programs |  | Preffered_Programs__c | Program
13 | Bank |  | Bank__c | Program
14 | Max# NSFs |  | Max_No_NSFs__c | Program
15 | Max. Amount |  | Max_Amount__c | Program
16 | Commission % |  | Commission_Percentage__c | Program
17 | Industry |  | Industry__c | Program
18 | Main Contact | Custom Field | Main_Contact__c | Account
19 | Name | Standard Field | Name | Account
20 | Submission | Custom Object | Submission__c
21 | Name | Standard Field | Name | Submission
22 | Contact |  | Contact__c | Submission
23 | Status |  | Status__c | Submission
24 | Funder |  | Funder__c | Submission
25 | Program |  | Program__c | Submission
26 | Email |  | Email__c | Submission
27 | Date Submitted |  | Date_Submitted__c | Submission
28 | Required Document | Custom Object | Required_Documents__c | Opportunity
29 | Program | Custom Field | Program__c | Required Document
30 | SubmissionWizard | Visualforce Page
31 | SubmissionWizardController | Apex Class
32 | SubmissionWizardControllerTest | Apex Class
33 | SubmissionWizard_SelectProgram | Custom Label
34 | Submission_BCCAddress | Custom Label
35 | Submission_CCAddress | Custom Label
36 | Submission_MailNotSent | Custom Label
37 | Submission_MailSent | Custom Label
38 | SubmissionWizard | Static Resource
39 | OppMultipleAttachment | Visualforce Page
40 | MultipleUploadController | Apex Class
Funding Application
Sr. No. | Name | Type | API Name | Parent | Description
1 | Legal Name | Custom Field | Legal_Name__c | Account
2 | DBA | Custom Field | DBA__c | Account
3 | Type of Entity | Custom Field | Type_of_Entity__c | Account
4 | Federal Tax ID# | Custom Field | Federal_Tax_ID_No__c | Account
5 | Legal Address | Custom Field | Legal_Address__c | Account
6 | Legal Address City | Custom Field | Legal_Address_City__c | Account
7 | Legal Address State | Custom Field | Legal_Address_State__c | Account
8 | Legal Address Zip | Custom Field | Legal_Address_Zip__c | Account
9 | Physical Address | Custom Field | Physical_Address__c | Account
10 | Physical Address City | Custom Field | Physical_Address_City__c | Account
11 | Physical Address State | Custom Field | Physical_Address_State__c | Account
12 | Physical Address Zip | Custom Field | Physical_Address_Zip__c | Account
13 | Phone | Standard Field | Phone | Account
14 | Cellular # | Custom Field | Cellular_No__c | Account
15 | Fax | Custom Field | Fax | Account
16 | Date Business Established | Custom Field | Date_Business_Established__c | Account
17 | Length of Ownership | Custom Field | Length_of_Ownership__c | Account
18 | Requested Amount of Funds | Custom Field | Amount_Requested__c | Opportunity
19 | Use of Proceeds | Custom Field | Use_of_Proceeds__c | Account
20 | Industry | Standard Field | Industry | Account
21 | Gross monthly Sales | Custom Field | Gross_monthly_Sales__c | Account
22 | Credit Card Sales | Custom Field | Credit_Card_Sales__c | Account
23 | Website | Standard Field | Website | Account
24 | Email | Custom Field | Email__c | Account
25 | Owner #2 Zip | Custom Field | Owner_2_Zip__c | Account
26 | SSN # (2) | Custom Field | SSN_2__c | Account
27 | Bank Name | Custom Field | Bank_Name__c | Account
28 | Bank Contact | Custom Field | Bank_Contact__c | Account
29 | Bank Phone | Custom Field | Bank_Phone__c | Account
30 | Business Name | Custom Field | Business_Name__c | Account
31 | Business Contact/Account # | Custom Field | Business_Contact_Account__c | Account
32 | Business Phone # | Custom Field | Business_Phone__c | Account
33 | Landlord/Mortgagee | Custom Field | Landlord_Mortgagee__c | Account
34 | Landlord Contact Name | Custom Field | Landlord_Contact_Name__c | Account
35 | Landlord Phone # | Custom Field | Landlord_Phone__c | Account
36 | Lease start date | Custom Field | Lease_start_date__c | Account
37 | Time Left On Lease | Custom Field | Time_Left_On_Lease__c | Account
38 | Monthly Payment | Custom Field | Monthly_Payment__c | Account
39 | Square Footage | Custom Field | Square_Footage__c | Account
40 | Ever used a Business Cash Advance? | Custom Field | Ever_used_a_Business_Cash_Advance__c | Opportunity
41 | Cash Advance Company | Custom Field | Cash_Advance_Company__c | Opportunity
42 | Balance | Custom Field | Balance__c | Opportunity
43 | Owner 1 | Custom Field | Owner_1__c | Opportunity
44 | Owner 2 | Custom Field | Owner_2__c | Opportunity
45 | Social Security Number | Custom Field | Social_Security_Number__c | Contact
46 | Drivers License | Custom Field | Drivers_License__c | Contact
47 | % Of Ownership | Custom Field | Of_Ownership__c | Contact
48 | Combination Key For Owner | Custom Field | Combination_Key_For_Owner__c | Contact
49 | Contact Roles | Custom Field | Contact_Roles__c | Contact
50 | FundingApplication | Visualforce Page
51 | FundingApplicationView | Visualforce Page
52 | FundingApplicationController | Apex Class
53 | FundingApplicationControllerTest | Apex Test Class
54 | Funding Application | Button on Opportunity |  | Opportunity
55 | Send Funding Application | Button on Opportunity |  | Opportunity
56 | Create PDF | Button on Opportunity |  | Opportunity
57 | FundingApplicationTemplateId | Custom Label
58 | Funding Application Form | Conga Template
59 | CongaButtonUrl | Custom Setting | CongaButtonUrl__c
60 | Funding Application>Set Combination Key For owner on Contact | WorkFlow Rule |  | Opportunity
61 | Set Combination Format For Owner | Workflow field Update |  | Opportunity
Offer Wizard
Sr. No. | Name | Type | API Name | Parent | Description
1 | Offer | Custom Object
2 | Opportunity |  | Opportunity__c | Offer
3 | Status |  | Status__c | Offer
4 | Send |  | Send__c | Offer
5 | Send Offer | Button on Opportunity |  | Opportunity
6 | CongaQueryId_Offer | Custom Label
7 | CongaEmailTemplate_Offer | Custom Label
8 | CongaEmailTemplate_Offer | Custom Label
9 | Offer | Conga Query
10 | Funding Application Template | Conga Email Template
11 | Offer | Conga Email Template
12 | TaskTrigger | Trigger
13 | ActivityCountHandler | Class
14 | CloudMyBizLogo | Static Resource
Progress Bar
Sr. No. | Name | Type | API Name | Parent | Description
1 | ProgressBarImg | Static Resource
2 | . | Field on Opportunity | Progress_Bar__c | Opportunity
3 | Progress Bar Icon | Field on Opportunity | Progress_Bar_Icon__c | Opportunity
Admin Page
Sr. No. | Name | Type | API Name | Parent | Status
1 | AdminPage | Visualforce Page
2 | AdminPageController | Apex Class
3 | Admin Accounting Setting | Custom Setting
4 | Admin Pipeline Setting | Custom Setting
5 | Admin Report Setting | Custom Setting
6 | Admin Setup Setting | Custom Setting
7 | AdminPageImg | Static Resource
Lead Scoring
Sr. No. | Name | Type | API Name | Parent
1 | DollarSymbolForLeadScore | Static Resource
2 | Lead Score Rating | Cutsom Field |  | Lead
Activity Count
Sr. No. | Name | Type | API Name | Parent
1 | ExcludedSubjects | Custom Setting | ExcludedSubjects__c
2 | Subject | Custom Setting field | Subject__c | ExcludedSubjects
3 | Activity Count | Custom Field | Activity_Count__c | Lead
4 | TaskTrigger | Trigger
5 | EventTrigger | Trigger
6 | ActivityCountHandler | Handler
7 | ActivityCountHandlerForOpportunity
8 | ActivityCountHandlerForOpportunityTest
Transaction Functionality
Sr. No. | Name | Type | API Name | Parent
1 | Transaction | Custom Object | Transaction__c
2 | Account | Custom Field | Account__c | Transaction
3 | Amount | Custom Field | Amt_Non_Hourly__c | Transaction
4 | Bank Acct | Custom Field | Bank_Depostied__c | Transaction
5 | Collection Method | Custom Field | Collection_Method__c | Transaction
6 | Contact | Custom Field | Contact__c | Transaction
7 | Date | Custom Field | Date__c | Transaction
8 | Hourly Rate | Custom Field | Hourly_Rate__c | Transaction
9 | Hours | Custom Field | Hours__c | Transaction
10 | Hours*Rate | Custom Field | Hours_Rate__c | Transaction
11 | Opportunity | Custom Field | Opportunity__c | Transaction
12 | Pmt Method | Custom Field | Pmt_Method__c | Transaction
13 | Screenshot | Custom Field | Screenshot__c | Transaction
14 | Status | Custom Field | Status__c | Transaction
15 | Total Amt | Custom Field | Total_Amt__c | Transaction
16 | Total Transaction Debits | Custom Field | Total_Transaction_Debits__c | Transaction
17 | Total Transaction Credits | Custom Field | Total_Transaction_Credits__c | Transaction
18 | Type | Custom Field | Type__c | Transaction
19 | No_Acount_or_Contact | Validation Rule |  | Transaction
20 | Credit | Record Type |  | Transaction
21 | Debit | Record Type |  | Transaction
22 | Transaction Layout (Credit) | Page Layout |  | Transaction
23 | Transaction Layout (Debit) | Page Layout |  | Transaction
24 | TransactionFieldSetColumn1 | Field Set |  | Transaction
25 | TransactionFieldSetColumn2 | Field Set |  | Transaction
26 | TransactionFieldSetColumn3 | Field Set |  | Transaction
27 | TransactionPage_new | Visualforce Page |  | Transaction
28 | TransactionController_New | Apex Class |  | Transaction
29 | Receivable | Custom Object | Receivable__c | Receivable
30 | Adjustment - Amt$ | Custom Field | Adjustment__c | Receivable
31 | Amount | Custom Field | Amount__c | Receivable
32 | Amount Due | Custom Field | Amount_Due__c | Receivable
33 | Amount Paid | Custom Field | Receivable_Amount_Paid__c | Receivable
34 | Date Paid | Custom Field | Date_Paid__c | Receivable
35 | Date Sent | Custom Field | Date_Sent__c | Receivable
36 | Due Date | Custom Field | Due_Date__c | Receivable
37 | Due From Account | Custom Field | Due_From_Account__c | Receivable
38 | Hours (Manual) | Custom Field | Hours__c | Receivable
39 | Opportunity | Custom Field | Opportunity__c | Receivable
40 | Price | Custom Field | Cost__c | Receivable
41 | Rate | Custom Field | Rate__c | Receivable
42 | Status | Custom Field | Status | Receivable
43 | Sum of Credit ($) | Custom Field | Sum_of_Credit__c | Receivable
44 | Sum of Fees | Custom Field | Fee_Sum_of_RollUp__c | Receivable
45 | Sum of Hours | Custom Field | Hours_Roll_Up__c | Receivable
46 | Total Invoice Amount | Custom Field | Price_Conga__c | Receivable
47 | Type | Custom Field | Type__c | Receivable
48 | Commission Layout | Page Layout |  | Receivable
49 | Payable | Custom Object | Payable__c
50 | Account | Custom Field | Account__c | Payable
51 | Amount(Roll Up) | Custom Field | Amount_Roll_Up__c | Payable
52 | Amount Due | Custom Field | Amount_Due__c | Payable
53 | Bill Amount Due | Custom Field | Bill_Amount_Due__c | Payable
54 | Bill Amount Paid | Custom Field | Bill_Amount_Paid__c | Payable
55 | Contact | Custom Field | Contact__c | Payable
56 | Date Paid | Custom Field | Date_Paid__c | Payable
57 | Due Date | Custom Field | Due_Date__c | Payable
58 | Memo | Custom Field | Memo__c | Payable
59 | Opportunity | Custom Field | Opportunity__c | Payable
60 | Payable Date | Custom Field | Payable_Date__c | Payable
61 | Status__c | Custom Field | Status__c | Payable
62 | Transaction Line Credit | Custom Object | Transaction_Line_Credit__c
63 | Amount | Custom Field | Amount__c | Transaction Line Credit
64 | Date | Custom Field | Date__c | Transaction Line Credit
65 | Memo | Custom Field | Memo__c | Transaction Line Credit
66 | Receivable | Custom Field | Receivable__c | Transaction Line Credit
67 | Transaction | Custom Field | Transaction__c | Transaction Line Credit
68 | Transaction Line Debit | Custom Object | Transaction_Line_Debit__c
69 | Amount | Custom Field | Amount__c | Transaction Line Debit
70 | Date | Custom Field | Date__c | Transaction Line Debit
71 | Memo | Custom Field | Memo__c | Transaction Line Debit
72 | Payable | Custom Field | Payable__c | Transaction Line Debit
73 | Transaction | Custom Field | Transaction__c | Transaction Line Debit
74 | BILL_DUE_AMT_LESS_THAN_DEBT_AMT_PAID | Validation Rule |  | Transaction Line Debit
75 | DEBIT_TRANS_AMT_MORE_THAN_ZERO | Validation Rule |  | Transaction Line Debit
76 | AMT_EXCEEDS_TRANS_TOTAL_AMT | Validation Rule |  | Transaction Line Credit
77 | INV_DUE_AMT_LESS_THAN_CRED_AMT_PAID | Validation Rule |  | Transaction Line Credit
78 | TRANS_AMT_MORE_THAN_ZERO | Validation Rule |  | Transaction Line Credit
79 | Transaction Line Credit Layout | Page Layout |  | Transaction Line Credit
80 | Transaction Line Debit Layout | Page Layout |  | Transaction Line Debit
81 | Update Receivable Record | Workflow Rule |  | Transaction Line Credit
82 | Update Receivable Paid Amount | Field Update | Update_Total_Amount_Paid
83 | Transaction Status to Paid | Workflow Rule |  | Transaction
84 | Update Transaction Status to Paid | Field Update | Update_Transaction_Status_to_Paid | Transaction
85 | Receivable Update Date Paid when Status is Paid | Workflow Rule
86 | Update Date Paid | Field Update
87 | Receivable Amount Paid - Update Status To Paid | Workflow Rule
88 | Receivable Status To Paid | Field Update
89 | Payable Amount Paid - Update Status To Paid | Workflow Rule
90 | Payable Status to Paid | Field Update
91 | TRAN_LINE_ITEM_AMT_EXCEEDS_TRAN_AMT | Custom Label
92 | Payable/Receivable Status | Custom Setting | Status__c
93 | Transaction_PaidAmountExceedRecDueAmt | Custom Label
94 | Transaction_BillPaidAmountExceedsBalanceAmount | Custom Label
95 | TransactionController | Apex Class
96 | Transaction | Visualforce Page
97 | Memo | Custom Field
98 | Screenshot | Custom Field
99 | TestTransactionController | Apex Class
100 | Transaction Status to pending | Workflow Rule
101 | Update Transaction Status to Pending | Field Update
102 | Receivable Update Date Paid | Workflow Rule
103 | Update Receivable Date Paid | Field Update
104 | Transaction_AmountPaidMustBePositive | Custom Label
105 | Transaction_TransactionAmountmustBeFilled | Custom Label
106 | Transaction_TransactionAmountMustBePositive | Custom Label
107 | Update Payable Date Paid | Workflow Rule
108 | Update Transaction line Debit Date | Field Update
109 | Update Payable Paid Date | Field Update
110 | Update Receivable Paid Date | Field Update
Banking and CC/Bank Summary
Sr. No. | Component | Type | API Name
1 | BankAccountWizardVF | Visualforce Page
2 | BankAccountWizard.cls | Apex Class
3 | BackAccountWizardSummaryVC.component | Component
4 | BankAccountWizardSummaryController.cls | Apex Class
5 | PendingItemsController.cls | Apex Class
6 | PendingItemsVF.page | Visualforce Page
7 | BankAccountWizardVC.component | Component
8 | Bank Stmts Entry Wizard | Custom Button | Bank_Stmts_Entry_Wizard
9 | CC/ Bank Summary | Custom Button | CC_Bank_Summary
10 | CC Sales Entry Wizard | Custom Button | CC_Sales_Entry_Wizard
11 | Bank Account | Custom Button | Bank_Account
12 | BankAccountWizardSummaryVF | Visualforce Page
13 | Bank Statements | Custom Object | Bank_Account__c
14 | Credit Card Sales | Custom Object | Credit_Card__c
15
16 | AutoCompleteResources.resource | Static Resource
17 | BankAssets_Resources.resource | Static Resource
18 | CloudMyBizLogo.resource | Static Resource
19 | DollarSymbolForLeadScore.resource | Static Resource
20 | DragDrop.resource | Static Resource
21 | ImagePlusMinus.resource | Static Resource
22 | Jquary.resource | Static Resource
23 | MyChartsMDPIcon.resource | Static Resource
24 | MyChartsZip.resource | Static Resource
Tabs
1 | BankEnhancedList | Visualforce Page
2 | AccountEnhancedList | Visualforce Page
Reports and Dashboards
1 | Lead and opportunity | Dashboard
2 | Accounting Payables and receivables | Dashboard
3 | Payables by Month | Report
4 | Receivables by Month | Report
5 | Receivables By Bank | Report
6 | Payables By Bank | Report
7 | Funded Opportunities | Report
8 | Lead by Status | Report
9 | Opportunities Per Week | Report
10 | Current Month Converted Leads | Report
11 | Current Month Opportunities | Report
12 | Current Month Leads | Report
13 | Receivables | Report
14 | Payables | Report
15 | Payables By Rep | Report
Report
Dependant Components(On App)
Opportunity Layout (Contains GridBuddy Page)
Dashboard Idea
1 | DashboardIdeas_DealsDashboard | Custom Label
2 | DashboardIdeas_CampaignsUrl | Custom Label
3 | DashboardIdeas_Admin | Custom Label
4 | DashboardIdeas_Syndication_Dashboard | Custom Label
5 | DashbaordIdeas_Renewal_Path_Url | Custom Label
6 | DashbaordIdeas_Commissions_Path_Url | Custom Label
7 | DashbaordIdeas_Dashboard_Path_Url | Custom Label
8 | DashboardIdeas_MyInbox | Custom Label
9 | Dashboard_page_Images | Static Resources
10 | MCA_Home | Visualforce Page
11 | MCAHomeController | Apex Class
12 | MCA Home | Custom Tab
Manage Renewal
1 | Account_Bank_Record_type_Id | Custom Label
2 | Manage Renewal Page | Visualforce Page
3 | MovingRenewal Controller | Apex Class
4 | Manage Renwal | Custom Tab
5 | ColorImg | Static Resource
6 | MovingRenewal_CreatedOppStage | Label
7 | MovingRenewal_SelectCheckboxErr | Label
8 | MovingRenewal_CreatedOppNextStep | Label
9 | MovingRenewal_ContractStage | Label
10 | MovingRenewal_ThankyouMsg | Label
11 | Contract > Set Current Balance and Current Balance Date | Workflow Rule
12 | Opportunity> Set Funding Amount on Amount Field | Workflow Rule
13 | MovingRenewal_FollowupTasksCreated | Label
14 | MovingRenewal_SaveSuccessful | Label
15 | Renewal Management Dashboard | Dashboard
Track Changes
Workflow Rule
| OpportunityTrigger | Trigger
| OpportunityHandler | Apex Class
App
MCA App

## Missing Items from Package
Sr. No. | Name | Data Type | Component Type | included in the next Imperial Advance Release | Comments
1 | Open Opportunities | Report |  | Yes
2 | Deal Performance Report | Report |  | Yes
3 | Opportunities Funded by ISO | Report |  | Yes
4 | SubmissionWizard | Static Resource for Thank you page in Manage Renewal |  | Yes
5 | colorImages | Static Resource |  | Yes | Namespace error.Need Fixes on Released org for Manage Renewal
6
7 | CongaEmailTemplate_Offer | Label |  | Yes
8 | CongaQueryId_Offer | Label |  | Yes
9 | OfferWizard_ErrorMsg | Label |  | Yes
10 | Send Offers | Button on Opportunity |  | No
11 | Account Layout | Layout |  | Yes
12 | LeadMCATrigger | Trigger |  | Yes
13 | LeadHandler | Apex Class |  | Yes
14 | LeadHandlerTest | Apex Class |  | Yes
15 | ProgressBarImg | Static Resource |  | yes | Namespace error.Need Fixes on Released org for Manage Renewal
| LoanCalculator | Visualforce Page
| LoanCalculatorController | Apex Class

## New changes developed on Demo o
Sr. No. | Name | Api name | Object | Data Type | Component Type | included in the next Imperial Advance Release | Comments
1 | Sales Rep | Sales_Rep__c | Lead | Lookup (Contact) | Custom FIeld | Yes
2 | Sales Rep | Sales_Rep__c | Opportunity | Lookup (Contact) | Custom FIeld | Yes
3 | Set Opportunity status | Set_Opportunity_Status__c | Lead | Checkbox | Custom FIeld | Yes
4 | Set Opportunity status | Set_Opportunity_Status__c | Opportunity |  | Custom FIeld | Yes
5 | Opportunity> Set Stage To "Application In" | Opportunity> Set Stage To "Application In" | Opportunity |  | Workflow rule | Yes
6 | Set Opportunity Stage | Set Opportunity Stage | Opportunity |  | Workflow Task | Yes
7 | SubmissionWizardController |  |  |  | Apex Class |  | Added ability to sort by column
| SubmissionWizard |  |  |  | Visualforce page
| ManageRenewal |  |  |  | Visualforce page |  | Added ability to sort by column
| MovingRenewalController |  |  |  | Apex Class

## Deployed Components15-Apr
Sr. No. | Name | Type | API Name | Dependent Objects | After Deployment | Deployment Status
1 | Program | Custom Object | Program__c |  |  | Deployed
2 | Submission | Custom Object | Submission__c |  |  | Deployed
3 | Required Document | Custom Object | Required_Documents__c |  |  | Deployed
4 | Offer | Custom Object |  |  |  | Deployed
5 | Transaction | Custom Object | Transaction__c |  |  | Deployed
6 | Receivable | Custom Object | Receivable__c |  |  | Deployed
7 | Payable | Custom Object | Payable__c |  |  | Deployed
8 | Transaction Line Credit | Custom Object | Transaction_Line_Credit__c |  |  | Deployed
9 | Transaction Line Debit | Custom Object | Transaction_Line_Debit__c |  |  | Deployed
10 | Bank Statements | Custom Object | Bank_Account__c
11 | Credit Card Sales | Custom Object | Credit_Card__c
12 | Opportunity |  |  |  | Conga Related Button: Email Funding App Send Offers Button(Contains CongaQueryId: Custom Label) | Deployed
13 | Account |  |  | Contract, Loan Balance, Programs |  | Deployed
14 | Contract |  |  |  |  | Deployed
15 | Lead |  |  |  |  | Deployed
16 | Payable Line Item
17 | Payment
18 | Custom Labels |  |  |  |  | Deployed
19 | CreateContract | Visualforce Page |  |  |  | Deployed
20 | CreateContractController | APex Class |  |  |  | Deployed
21 | OppMultipleAttachment | Visualforce Page |  |  |  | Deployed
22 | MultipleUploadController | APex Class |  |  |  | Deployed
23 | SubmissionWizard | Visualforce Page |  |  |  | Deployed
24 | SubmissionWizardController | APex Class |  |  |  | Deployed
25 | SubmissionWizardControllerTest | APex Class |  |  |  | Deployed
26 | TaskTrigger | Apex Trigger |  |  | Commented UpdateOffers method | Deployed
27 | ActivityCountHandler | Apex Class |  |  | Commented UpdateOffers method | Deployed
28 | ActivityCountHandlerForOpportunity | Apex Class |  |  |  | Deployed
29 | ActivityCountHandlerForOpportunityTest | Apex Class |  |  |  | Deployed
30 | EventTrigger | Apex Trigger |  |  |  | Deployed
31 | AdminPage | Visualforce Page |  |  |  | Deployed
32 | AdminPageController | Apex Class |  |  |  | Deployed
33 | AdminPageControllerTest | Apex Class |  |  |  | Deployed
34 | Transaction | Visualforce Page |  |  |  | Deployed
35 | TransactionController | Apex Class |  |  |  | Deployed
36 | TestTransactionController | Apex Class |  |  |  | Deployed
37 | TransactionPage_new | Visualforce Page |  |  |  | Deployed
38 | TransactionController_new | Apex Class |  |  |  | Deployed
39 | Dashboard_Ideas | Visualforce Page |  |  |  | Deployed
33 | DashboardIdeasController | Apex Class |  |  |  | Deployed
34 | ManageRenewalPage | Visualforce Page |  |  |  | Deployed
35 | MovingRenewalController | Apex Class |  |  |  | Deployed
36 | OpportunityTrigger | Apex Trigger |  |  |  | Deployed
37 | OpportunityHandler | Apex Class |  |  |  | Deployed
| CloudMyBizLogo | Static Resource |  |  |  | Deployed
| AdminPageImg | Static Resource |  |  |  | Deployed
| Dashboard_page_Images | Static Resource |  |  |  | Deployed
| SubmissionWizard | Static Resource |  |  |  | Deployed
| ProgressBarImg | Static Resource |  |  |  | Deployed
| ColorImg | Static Resource |  |  |  | Deployed
| Admin Accounting Setting | Custom Setting |  |  |  | Deployed
| Admin Pipeline Setting | Custom Setting |  |  |  | Deployed
| Admin Report Setting | Custom Setting |  |  |  | Deployed
| Admin Setup Setting | Custom Setting |  |  |  | Deployed
| ExcludedSubjects | Custom Setting |  |  |  | Deployed
| Contact | Standard Object |  |  |  | Deployed
| AccountLookupController | Apex Class |  |  |  | Deployed
| AccountLookupVC | Component |  |  |  | Deployed
| AccountLookupVF | Visualforce Page |  |  |  | Deployed
| BankEnhancedList | Visualforce Page |  |  |  | Deployed
| ISO | Custom Tab |  |  |  | Deployed
| Bank | Custom Tab |  |  |  | Deployed
| Open Submissions By Bank | Report |  |  |  | Deployed
| Opportunity By Stage | Report |  |  |  | Deployed
| Submission By banks | Report Type |  |  |  | Deployed
| Opportunity with submissions | Report |  |  |  | Deployed
| Approved Submission by Banks | Report |  |  |  | Deployed
| Opportunity with submissions and Offers | Report |  |  |  | Deployed
| Submissions by Rep | Report |  |  |  | Deployed
| Offer by Bank | Report Type |  |  |  | Deployed
| Avg Offers by Bank | Report |  |  |  | Deployed
| Declines Submission by Bank | Report |  |  |  | Deployed
| Deal Management | Dashboard
| Payable By Month | Report |  |  |  | Deployed
| Receivable by Month | Report |  |  |  | Deployed
| Syndication Dashboard | Dashboard
| Syndication | Custom Object |  |  |  | Deployed
| Syndication With Amounts | Report |  |  |  | Deployed
| Syndication by Syndication Amount | Report |  |  |  | Deployed
| Syndication by Syndication % | Report |  |  |  | Deployed
| Syndication By Disbursement Schedule | Report |  |  |  | Deployed
| Syndication by Deal Funding Amount | Report |  |  |  | Deployed
| Syndication By Bank | Report |  |  |  | Deployed
| Syndication by Opportunity | Report |  |  |  | Deployed
| Campaign Metrics Dashboard | Dashboard |  |  |  | Deployed
| Company Performanece Dashoboard | Dashboard |  |  |  | Deployed
| All campaign leads this month | Report |  |  |  | Deployed
| Top 5 campaigns by revenue | Report |  |  |  | Deployed
| Campaign ROI by type | Report |  |  |  | Deployed
| Leads by lead source | Report |  |  |  | Deployed
| Pipeline generated by campaigns this FY | Report |  |  |  | Deployed
| Win % by campaign | Report |  |  |  | Deployed
| Campaign leads generated per month | Report |  |  |  | Deployed
| lead conversion ratio by user | Report |  |  |  | Deployed
| Top ten caompaign opportunities | Report |  |  |  | Deployed
| Converted leads value this year | Report |  |  |  | Deployed
| Campaign leads by industry | Report |  |  |  | Deployed
| Leads created per calendar year | Report |  |  |  | Deployed
| leads converted into opports per month | Report |  |  |  | Deployed
| Campaign responses by type | Report |  |  |  | Deployed
| Closed Sales | Report |  |  |  | Deployed
| Leads by Lead Source | Report |  |  |  | Deployed
| Open Cases By Priority | Report |  |  |  | Deployed
| Open Deals | Report |  |  |  | Deployed
| Sales Leaderboard | Report |  |  |  | Deployed
| Top Accounts | Report |  |  |  | Deployed
| Leads by Status | Report |  |  |  | Deployed
| Cases Status by Rep | Report |  |  |  | Deployed
| Month to Date Trending | Report |  |  |  | Deployed
| Sales Pipeline by Stage | Report |  |  |  | Deployed
| Solutions Added | Report
| FundingApplication Controller | Apex Class |  |  | Commented Conga related buttons
| FundingApplicationView | Visualforce Page
| FundingApplication | Visualforce Page
| Activities by Salesperson | Report
| Marketing Exec # of Leads | Report
| Marketing Exec Amount per Camp | Report
| Marketing Exec Campaign ROI by Camp Type | Report
| Marketing Exec Campaigns by ROI | Report
| Marketing Exec Conversion Rate | Report
| Marketing Exec Converted Amount | Report
| Marketing Exec Converted and Won Amount | Report
| Marketing Exec Converted by Month | Report
| Marketing Exec Lead Trends by Status | Report
| Marketing Exec Leads by Campaigns | Report
| Marketing Exec Leads by Industry | Report
| Marketing Exec Leads by Source | Report
| Marketing Exec Leads Converted | Report
| Sales Exec Bookings Trend | Report
| Sales Exec Closed Deals by Owner | Report
| Sales Exec Lost Deals | Report
| Sales Exec Closed Deals QTD | Report
| Sales Exec Open Deals | Report
| Sales Exec Open Pipeline next 90 days | Report

## Deployment Plan 07-05-2014
Sr. No. | Name | Data Type | Component Type | Parent | Status | Date of Deployment
1 | TransactionController |  | Apex Class |  | Deployed to release org | 2014-05-08
2 | TransactionController_new |  | Apex Class |  | Deployed to release org | 2014-05-08
3 | TransactionPage |  | Visualforce Page |  | Deployed to release org | 2014-05-08
4 | TransactionPage_new |  | Visualforce Page |  | Deployed to release org | 2014-05-08
5 | TestTransactionController
6 | ManageRenewal |  | Visualforce Page |  | Deployed to release org | 2014-05-08
7 | MovingRenewalController |  | Apex Class |  | Deployed to release org | 2014-05-08
8 | MovingRenewal_ThankyouMsg |  | Custom label |  | Deployed to release org | 2014-05-08
9 | CreateContract |  | Visualforce Page
10 | CreateContractController |  | Apex Class
11 | CreateContractControllerTest |  |  |  | Deployed to release org | 2014-05-09
12 | SubmissionWizard |  | Page
13 | SubmissionWizard Controller |  | Class
14 | Account |  | Object |  | Deployed to release org | 2014-05-08
15 | LeadMCATrigger |  | Trigger |  | Deployed to release org | 2014-05-09
16 | LeadHandler |  | Apex Class |  | Deployed to release org | 2014-05-09
17 | LeadHandlerTest |  | Apex Class |  | Deployed to release org | 2014-05-09
18 | CreateContract_CannotSkipOffer |  | Custom label
19 | FundingApplication |  | Page
20 | FundingApplicationView |  | Page
21 | FundingApplicationController |  | Classes

## PreInstallation Steps
S.no
1 | Changes in Deal Entry Wizard custom button on Opportunity | In Deal Entry Wizard custom button, append the namespace for below mentioned terms: 1. Submission__c object and its field Opportunity__c 2. Offer__c and its field Opportunity__c 3. CreateContract page in window.open() method
2 | Changes in Submission Wizard custom button on Opportunity | change the name of SubmissionWizard page used in url
3 | Changes in Send Offers custom button on Opportunity | Change in query to get Opportunity with their related Offers: Append the namespace for following: 1. Offers object name and its custom fields i.e Send__c, Status__c
4 | Changes in Funding Application custom button on Opportunity | Change the name of FundingApplication page used in url

## Post Installation Steps
Sr. No | Labels | Value | Status
1 | ISOListId | Add the list Id of ISO in the Label | Complete
2 | BankListId | Add the list Id of Bank in the Label | Complete
3 | Account_Bank_Record_type_Id | Add the Id of "Bank" Record Type | Complete
4 | DashbaordIdeas_Commissions Path Url | Add the Id of Accounting - Receivables & Payables dashboard | Complete
5 | DashbaordIdeas_Dashboard_Path_Url | Add the Id of dashbaord home page. | Complete
6 | Dashbaord_Renewal_Path_Url | Add the path of Manage Renewal page. | Complete
7 | DashboardIdeas_Admin | Add the path of Admin page | Complete
8 | DashboardIdeas_CampaignsUrl | Add the Id of Campaign Metrics Dashboard | Complete
9 | DashboardIdeas_DealsDashboard | Add the Id of Deal Management dashboard | Complete
10 | DashboardIdeas_Syndication_Dashboard | Add the Id of syndication dashbaord page | Complete
11 | FundingApplicationTemplateId | Add the Id of Funding Application template | Complete
12 | CongaTemplateId | Add the Id of FUnding Application Template Id | Complete
13 | MCA_Home_Task_Activities_Management_Dashboard | Change the sales activity dashboard id to the same dashboard of current org Id | Complete
14 | Create record for Custom Setting used in custom setting |  | Complete
15 | Need to set packaged page layout on Opportunity object
16 | Need to set packaged page layout on lead object
17 | Need to change picklist values on Opportunity stage fields
18 | Change in Custom Label of MCA Home - DashboardIdeas_MyInbox | Chage the link to Activities tab link
19 | Acct Record type: Change default on Accounts to merchants.