## Summary
Engagement Effort Summary					Activity	Total / Effort	Weekly/Monthly Schedule					Go-Live	Warranty/Support
No	Project Phase	%	Efforts (Hrs)				W1	W2	W3	W4	W5	W6		W7	W8
1	Project Management	4%	1		Project Management	1	1
2	RA & Solution Design	4%	1		RA & Solution design	1	1
3	Development & Unit testing	77%	23		Development	23	23	0
4	Integration and System Testing	10%	3		Integration and System testing	3	3	0
5	Deployment & Documentation	2%	1		Deployment & Documentation	1	1	0
6	UAT Support, Go-Live	3%	1		UAT Support, Go-Live	1					8	8
7	Live rollout support [warranty period 2 weeks]	0%	0		Live rollout support	0					8	8
Total Project Efforts		100%	30		0	30	29.0	0.0					1	1
Total Engagement Efforts			30		Resources		1
Blended Rate (USD Per Hour)
Cost (USD)			$-

## WBS
Item No.	Item Description	Category	Solution Overview	Complexity Level	POC Efforts	Development Efforts(Hrs)	Assumptions
MCA-01	Create field sets	Configuration	1. Create 6 field sets for 6 sections on funding application page. / 2. Add fields in field sets for each section	Simple		2	1. Page sections will remain same. / 2. Security settings will be applicable for fields displayed on Funding application page
MCA-02	Reference FieldSets on visualforce Page.	Development	1. Update logic of Funding Application Visual-force Page to reference field sets. / 2. Change the existing logic of Funding Application Visual-force page to dynamically display fields in each section of funding application page. / 3. Adjust the CSS changes	Complex		6	1. Page sections will remain same. / 2. Security settings will be applicable for fields displayed on Funding application page
MCA-03	Update Funding Application Controller	Development	1. Update existing logic of funding application controller using / Field set values	Medium		5	1. Page sections will remain same. / 2. Security settings will be applicable for fields displayed on Funding application page
MCA-04	Update Functionality of buttons / 1. Quick Save / 2. Save	Development	1. Update logic of two buttons to save field sets values	Medium		3	1. Page sections will remain same. / 2. Security settings will be applicable for fields displayed on Funding application page
MCA-05	Unit testing	Development	1. Perform unit testing of whole functionality	Medium		3	1. Page sections will remain same. / 2. Security settings will be applicable for fields displayed on Funding application page
MCA-61	Update Test Class	Development	1. Updating test class logic considering scenarios of / Newly updated code	Medium		4	1. Page sections will remain same. / 2. Security settings will be applicable for fields displayed on Funding application page
						23