## Summary
Engagement Effort Summary |  |  |  | Activity | Total Effort | Weekly/Monthly Schedule | [5 empty] | Go-Live | Warranty/Support
No | Project Phase | % | Efforts (Hrs) |  |  | W1 | W2 | W3 | W4 | W5 | W6 |  | W7 | W8
1 | Project Management | 3% | 2 | Project Management | 2 | 1 | 1
2 | RA & Solution Design | 0% | 0 | RA & Solution Design | 0
3 | Development & Unit testing | 80% | 45 | Development | 45 | 40 | 5
4 | Integration and System Testing | 15% | 8 | Integration and System testing | 8 |  | 8
5 | Deployment & Documentation | 2% | 1 | Deployment & Documentation | 1 |  | 1
6 | UAT Support, Go-Live | 0% | 0 | UAT Support, Go-Live | 0
7 | Live rollout support [warranty period 2 weeks] | 0% | 0 | Live rollout support | 0 | [8 empty] | 0
Total Project Efforts |  | 100% | 56.25 | 0 | 56 | 41 | 15 | [5 empty] | 1 | 1
Total Engagement Efforts |  |  | 56 | Resources |  | 2 | 2
Blended Rate (USD Per Hour)
Cost (USD) |  |  | 0

## WBS
Item No. | Item Description | Category | Solution Overview | Complexity Level | POC Efforts | Development Efforts(Hrs) | Assumptions
1 | Sales History | Custom Development | Visualforce page with a read only grid to display Bank Statement and Credit Card Sales | Simple |  | 4
2 | Submission | Custom Development | Visualforce page with a editable grid to display Submission records | Simple |  | 4
3 | Offer | Custom Development | Visualforce page with a editable grid to display Offer records | Simple |  | 3
4 | Stips | Custom Development | Visualforce page with a editable grid to display Stips records | Simple |  | 3
5 | Commissions | Custom Development | Visualforce page with a editable grid to display Commission and the associated Payable, Payable Line Item, Receivable, Receivable Line Item Summary records | Medium |  | 12
6 | Syndication | Custom Development | Visualforce page with a editable grid to display Syndication records | Simple |  | 3
7 | Loan Balance | Custom Development | Visualforce page with a editable grid to display Loan Balance records | Simple |  | 3
8 | Contact Roles | Custom Development | Visualforce page with a editable grid to display Contact Roles records | Simple |  | 3
9 | Task | Custom Development | Visualforce page with a editable grid to display Task records | Simple |  | 2
10 | Test Code Development | Custom Development | Apex test code for the developed business logic | Medium |  | 8
45