## Summary
Engagement Effort Summary |  |  |  | Activity | Total Effort | Weekly/Monthly Schedule |  |  |  |  | Go-Live | Warranty/Support
No | Project Phase | % | Efforts (Hrs) |  |  | W1 | W2 | W3 | W4 | W5 |  | W7 | W8
1 | Project Management | 8% | 9 | Project Management | 9 | 3 | 3 | 3
2 | RA & Solution Design | 15% | 6 | RA & Solution design | 6 | 6
3 | Development & Unit testing | 70% | 60 | Development | 60 | 25 | 40 | 7
4 | Integration and System Testing | 0% | 0 | Integration and System testing | 0
5 | Deployment & Documentation | 7% | 4 | Deployment & Documentation | 4 |  |  | 4
6 | UAT Support, Go-Live |  | 4 | UAT Support, Go-Live | 4 |  |  |  | 4 |  |  | 8 | 8
7 | Live rollout support [warranty period 2 weeks] |  | 0 | Live rollout support | 0 | [6 empty] | 8 | 8
Total Project Efforts |  | 100% | 85.7143 | 0 | 83 | 34 | 43 | 14 | 4 | 0 |  | 1 | 1
Total Engagement Efforts |  |  | 89.7143 | Resources |  | 2 | 1 | 2 | 1 | 1
Blended Rate (USD Per Hour)
Cost (USD)

## WBS
Item | Name | Duration (Hrs) | Start | Finish | Predecessors | Assumptions
| MCA App Packaging | 19.5 | 2014-03-27 | 2014-03-28
1 | Deployment of the Base Package functionalities to the MCA Pcakaging Org | 7 | 2014-03-27 | 2014-03-27
2 | Creating Base package for Core MCA Functionalities | 5 | 2014-03-27 | 2014-03-28 | 1
3 | Installation of Core Package on the Extensions Packaging Org | 1.5 | 2014-03-28 | 2014-03-28 | 2
4 | Deployment of Extensions Component and creating package Extensions | 6 | 2014-03-31 | 4/31/2014 | 3
| Lead Management | 13 | 2014-03-27 | 2014-03-28
5 | Custom Fields, Page Layouts and List Views | 4 | 2014-03-27 | 2014-03-27
6 | Lead Assignment Rules | 3 | 2014-03-27 | 2014-03-27
7 | Quick Create Lead Chatter Action | 1 | 2014-03-27 | 2014-03-27
8 | Workflow Development for Leads (x2) | 3 | 2014-03-28 | 2014-03-28 | 5
9 | Web to Lead form generation | 2 | 2014-03-28 | 2014-03-28 | 5
| Campaign Management | 4 | 2014-03-28 | 2014-03-31
10 | Campaign Member Lists and Tracking | 1 | 2014-03-28 | 2014-03-28
11 | Creating Marketing Campaigns | 1 | 2014-03-28 | 2014-03-28 | 5
12 | Lead Source Tracking | 1 | 2014-03-28 | 2014-03-28 | 5
13 | ROI Monitoring | 1 | 2014-03-31 | 2014-03-31 | 10,11,12
| Opportunity Management | 6 | 2014-03-31 | 2014-03-31
14 | Add new fields Create Page Layouts and List Views | 2 | 2014-03-31 | 2014-03-31 | 1
15 | Opportunity Stages Modifications | 1 | 2014-03-31 | 2014-03-31 | 1,14
16 | Workflow Development for Opportunity (x2) | 3 | 2014-03-31 | 2014-03-31 | 1, 14, 15
| Business Logic | 8 | 2014-04-04 | 2014-04-04
17 | Create 10 Validation Rules | 2 | 2014-04-04 | 2014-04-04
18 | Create 10 Formula Fields | 2 | 2014-04-04 | 2014-04-04
19 | Create 5 Text format email templates | 1 | 2014-04-04 | 2014-04-04
20 | Create 5 Custom list views per object | 1 | 2014-04-04 | 2014-04-04
21 | Create 20 Custom fields per object | 2 | 2014-04-04 | 2014-04-04
| 3rd Party Applications | 4 | 2014-04-01 | 2014-04-01
22 | Application Installation from AppExchange - Conga, Laser Credit and Grid Buddy | 4 | 2014-04-01 | 2014-04-01
| Funding Application Conga Template | 8 | 2014-04-01 | 2014-04-02
23 | Create Funding Application Conga Form Template | 8 | 2014-04-01 | 2014-04-02 | 1, 10, 14, 22
| Reports and Dashboards | 9 | 2014-04-03 | 2014-04-03
24 | Install AppExchange Reports and Dashboards packages and minor customizations. | 3 | 2014-04-03 | 2014-04-03
25 | Create up to 10 Reports and Dashboard Components to client’s requirements | 6 | 2014-04-03 | 2014-04-03 | 1, 10, 14, 23, 24
| Total | 72