## MCA Issues 6 May 2014
Sr. No. | Task | Owner | Effort (Hrs.) | Issue Type | Status | Query
1 | Deal Entry: There is an issue with the Bank name on the Wizard (When you choose an offer, the screen shows the incorrect bank at the top header section). | Sneha | 0.15 | Bug | Closed
2 | Deal Entry: The “bank” lookup field should update the opportunity and not contract object | Sneha | 0.15 | CR | Closed
3 | Opportunity: The related lists on opportunity keep showing up on the standard page layout, even after many times that I remove them from the page. What is this happening? | Sneha | 0.15 | Bug | Closed
4 | Acct Record type: Change default on Accounts to merchants. | Sneha | 0.15 | CR | Closed
5 | Deal Entry Wizard: Deal type should be populated onto the opportunity from the Deal entry wizard. (Currently, it is left blank) | Sneha | 0.15 | CR | Closed
6 | Contract: Balance info on Contract should be populated from the payback amount upon funding | Sneha | 1 | CR | Open | When should the Balance be populated on a Contract from the Opportunity's Payback Amount? As per my understanding it should be done when the Contract is generated.
7 | Opp Field: "# Bank Stmt" & "# Credit Card Stmts" fields on opportunity are not calculating properly on the Opportunity. | Sneha | 0.25 | Bug | Open | What should be the business logic to calculate the Bank Statement and Credit Card Statements? Should it be a rollup of the count of Bank Statement and Credit Card Statement records? The existing effort assumes formula changes but if a rollup is required it would require and Apex trigger and hence the effort would change.
8 | Add a Transation line item column for Status | Shraddha | 0.15 | CR | Closed
9 | Transactions: Remove “Type” field from Transactions page. Delete the field. | Shraddha | 0.15 | CR | Closed
10 | Transactions: Transaction Status should remain Incompleted until there are line items that add up to the full amount of the transaction. | Shraddha | 0.3 | CR | Open | Should this status be Incomplete or Pending? This conflicts with point # 12 i.e missing line items should reqult in a common status either "Pending" or "Incomplete"
11 | Transactions: The Edit button should be overwritten with the Visualforce page. | Shraddha | 6 | CR | Open | This would require a significant code change in the controller and test code
12 | Transactions: When a transaction line item is deleted, it should mark the Transaction Status as pending and Payable/receivable status should update as open/unpaid | Shraddha | 12 | CR | Open | Have to write two triggers on Transaction Line Item Credit and Transaction Line Item Debit with test class
13 | Transactions: Then choosing transaction line items with the VF page, it adds/created transaction line items even when you un-click the receivable/payable. It seems that once you click on it once, it will create line items upon save. | Shraddha | 1.3 | Bug | Closed | This would require a significant code change in the controller and test code
14 | Renewal - Thank you Screen. Please update message. | Neena | 0.3 | CR | Closed
15 | Error on Grid - MCA App Demo | Neena | 0.3 | CR | Closed
16 | Records not being committed to the database on Save | Sneha | 1 | Bug | Open
17 | List index Out of bound | Sneha | 1.3 | Bug | Open
Total Effort (Hrs.) |  |  | 24.8