## Sheet1
Sr. No. | Task | Owner | Effort (Hrs) | Done by 3 April, 2014 | Query
1 | Renewals |  | 26 |  | These 26 hours are the additional effort that would be required
1.1 | Create Contract changes wireframe to display 4 Screens – There should be 4 screens: 1. Offers 2. Deal Info (Funding Amt etc). 3. Commissions Payable & Syndication 4. Preview Screen of all the info. Please send wireframe on this | Sneha | 8 | No | 1. What fields need to be included on the Commissions Payable and Syndication screen? Should they be the same as on Transaction Line Items screen. What functionality shoudl this screen contain - Create / Edit or View Only2. The provided effort is for preparing the wireframes only. The said 8 hours have already ben consumed on ove rand above the discussed 48 hours effort for Renewals.
1.2 | Track changes Trigger on Opportunity - When the Opportunity Payback Amount is updated after the Contract is created then update the Stage to 'Eligible for Renewal' if it satisfies the Criteria Renewal Eligibility % >= Paid% | Sneha | 5 | No | 1. Is there a possibility of the Payback Amount changing after the Contract is generated. I believe that it shoudldn't but please confirm.
1.3 | Manage Renewals Page changes - Adding Slider to the page - Adding Chatter | Ajay | 10 | No | 1. For chatter do we need to include the UI for posting a chatter feed on the page or should it be the live agent window. We ahave attached a screenshot on the Trello ticket. Please confirm
1.4 | Renewal - Add Paid % | Ajay | 3 | Yes
2 | Count # of Tasks / Events for Opportunity | Ajay | 8 | Yes
3 | Dashboards Idea Page | Neena | 10 | Yes
4 | Submission Wizard - Updates | Sneha | 4 | Yes | All changes except using templates for Submission wizard would be completed. We would be taking the template as a phase 2 item
5 | Funding email changes | Sneha | 2 | Yes
6 | Setup Forecasts for Demo | Shraddha | 1 | No | We have logged a case on the Salesforce portal for this and we have not received a reply for this.
8 | Making changes for Transaction on CMB org | Shraddha | 3.5 | Yes
Total Effort (in Hours) |  |  | 54.5